## Sheet1
ASMC Analysis
No | Modules | Changes | Time(min) | Charges(USD) | Status | Confirm
1 | Changes needed: | all date format change to dd-mmm-yyyy, example 10-Jul-2016 for all date in the CRM | 60 | 300 | Done
2 |  | all currency format make sure in this format (100,000.00) | 60 | 300 | Done
3 |  | all tables in the CRM changed to datatable (able to export excel, pdf, print), able to search | 480 | 2400 | Undone
4 |  | all word ‘customer’ in the CRM change to ‘Funder’ | 60 | 300 | Undone
5 | signup form | admin, agent or manager or director also can submit the form | 60 | 300 | Undone
6 |  | if login as agent, manager or director, the form will hide the field: “Booking Ref. Number”, only admin can enter this | 15 | 75 | Undone
7 |  | after submit allow 3 days to edit, list the form submitted in another page accessible within 3 days. | 480 | 2400 | Undone
8 |  | within 3 days they still can update the record. after 3 days the record will be hidden (unless enable by admin) | 240 | 1200 | Undone
9 |  | after 3 days, only admin can enable the form to be edited by them again | 240 | 1200 | Undone
10 |  | admin can enable or disable editing of the form submitted | 60 | 300 | Undone
11 |  | when key in customer NRIC, auto search database for existing customer with the NRIC and auto fill the form with customer info | 240 | 1200 | Undone
12 |  | for new customer system will auto generate password and send to admin, funder, agent and director when the form is submitted | 240 | 1200 | Undone
13 |  | if funder account doesn't have email, don’t need to send to funder | 30 | 150 | Undone
14 |  | when add new a customer record manually from CRM also send the auto generate password to customer/funder email | 240 | 1200 | Undone
15 | Manger login | under list agent, remove/hide the column agent code, manager name | 30 | 150 | Undone
16 |  | add another column to indicate active/not active (under agent profile can mark the agent as active or not active) | 30 | 150 | Undone
17 |  | under funding record - remove the column manager | 30 | 150 | Undone
18 |  | funding record table add a filter by agent drop down | 30 | 150 | Undone
19 |  | commission table - all word ’invoices' change to ‘contracts’ | 30 | 150 | Undone
20 |  | commission table - add a filter by agent drop down | 30 | 150 | Undone
21 |  | commission payout date wrong | 30 | 150 | Undone
22 | agent login | under funding record, all customer name should be capital letter | 30 | 150 | Undone
23 |  | remove the column agent & manager | 30 | 150 | Undone
24 |  | commission table, the field 'invoice' change to 'contract', hide agent column | 30 | 150 | Undone
25 |  | add a filter by customer drop down | 30 | 150 | Undone
26 |  | under commission table each column under the date should be $currency format (example 100,000.00), same to the total row | 30 | 150 | Undone
27 |  | funding record table, hide manager column | 30 | 150 | Undone
28 |  |  |  | 0
29 |  |  |  | 0
30 |  |  |  | 0
31 |  |  |  | 0
|  | Total min | 2895
|  | Total hour and charges | 48.25 | 241.25